## Sheet1
DORA ALLOCATION 2022 2023
DESCRIPTION | 2022/23 | 2023/24 | 2024/25
EQUITABLE SHARES | 202071000 | 223270000 | 246827000
FMG | 1650000 | 1700000 | 1700000
EPWP | 1292000
MIG | 59592000 | 51727000 | 53999000
ENERGY EFFECIENCY AND DEMAND SIDE MANAGEMENT GRANT | 4000000 |  | 5000000
INEP | 20000000 | 22500000 | 10971000
WSIG SCHEDULE 5B | 0 | 50832000 | 52209000
WSIG SCHEDULE 6B | 67160000 | 71226000 | 63531000
TOTAL ALLOCATIONS | 355765000 | 421255000 | 434237000
| 0 | 0 | 0

## CAPEX 2023-2024
PROJECT NAME MIG | DEPARTMENT | 2023/24 | 2024/25 | 2025/26 | SOURCE OF FUNDING
Extension and Augmentation of water supply in Witpoort RWS 6 | MIG | 3892681.9 | 0 | 0 | MIG
Establishment of transfer stations in the rural villages | MIG | 31980275.36 | 0 | 0 | MIG
Marapong sports, arts and culture precinct phase 2 | MIG | 10000000 | 0 | 0 | MIG
Highmast installation in Various villages | MIG | 3267692.94 | 11316727.78 | 0 | MIG
Martinique access road | MIG |  | 8000000
Letlora access road | MIG |  | 5000000 | 8000000 | MIG
Extension 1 and Augmentation of water supply in Mokuruanyane Cluster | MIG |  | 11139709.42 | 0 | MIG
Steve Biko EXT2 access road | MIG |  | 5771137 | 14182600 | MIG
Bangalong access road | MIG |  |  | 16348000 | MIG
Construction of OR tambo | MIG |  | 5000000 | 15000000 | MIG
Marapong Acess Roads & storm water | MIG |  | 5059126 |  | MIG
TOTAL MIG |  | 49140650.2 | 51286700.2 | 53530600
PROJECT NAME WSIG | DEPARTMENT | 2023/24 | 2024/25 | 2025/26 | SOURCE OF FUNDING
REPLACEMENT OF ASBESTOS CEMENT PIPE (AC) TO HDPE/uPVC WATER PIPES IN LEPHALALE TOWN (RESIDENTIAL) | WSIG |  | 13052250 | 13633250 | WSIG
REPLACEMENT OF ASBESTOS CEMENT PIPE (AC) TO HDPE/uPVC WATER PIPES IN ONVERWACHT (CBD) | WSIG |  | 13052250 | 13633250 | WSIG
REPLACEMENT OF ASBESTOS CEMENT PIPE (AC) TO HDPE/uPVC WATER PIPES IN LEPHALALE | WSIG |  | 13052250 | 6816625 | WSIG
REPLACEMENT OF ASBESTOS CEMENT PIPE (AC) TO HDPE/uPVC WATER PIPES IN MARAPONG (ZONE 2) | WSIG |  | 13052250 | 13633250 | WSIG
REPLACEMENT OF ASBESTOS CEMENT PIPE (AC) TO HDPE/uPVC WATER PIPES IN ONVERWACHT (SECTION C) | WSIG S6B |  | 15882775 | 17500000 | WSIG
REPLACEMENT OF ASBESTOS CEMENT PIPE (AC) TO HDPE/uPVC WATER PIPES IN MARAPONG (ZONE 1) | WSIG S6B |  | 15882775 | 17500000 | WSIG
REPLACEMENT OF ASBESTOS CEMENT PIPE (AC) TO HDPE/uPVC WATER PIPES IN ONVERWACHT (SECTION A) | WSIG S6B |  | 15882775 | 17500000 | WSIG
REFURBISHMENT AND UPGRADING OF SEWER PUMP STATIONS, WASTE WATER TREATMENT WORKS, NETWORK PIPES AND REPLACEMENT OF SEWER AC PIPES | WSIG |  |  | 6816625 | WSIG
Marapong Bulk Water Supply | WSIG S6B | 21226000 |  |  | WSIG
Marapong Storage Facility-Construction of 2x3ML Steel Reservoirs | WSIG S6B | 10000000 | 15882775 | 17500000 | WSIG
TOTAL WSIG |  | 31226000 | 115740100 | 124533000
PROJECT NAME RENERGY EFFICIENCY | DEPARTMENT | 2023/24 | 2024/25 | 2025/26 | SOURCE OF FUNDING
Energy Efficiency 5A | Electrical | 0 | 5000000 |  | Energy Efficiency 5A
PROJECT NAME ELECTRIFICATION | DEPARTMENT | 2023/24 | 2024/25 | 2025/26 | SOURCE OF FUNDING
Electrification in Various villages - 5A | Electrical | 0 | 18000000 | 18806000 | Electrification
TOTAL ELECTRIFICATION |  | 0 | 18000000 | 18806000 | 0
PROJECT NAME OWN FUNDING | DEPARTMENT | 2023/24 | 2024/25 | 2025/26 | SOURCE OF FUNDING
Asbestos Cutting Machine | Water | 100000 |  |  | LLM
Jack Hammer (Makita Demolition Hammer) | Water | 150000 |  |  | LLM
Palisade Fencing for Storage Facilities and Water Pumpstations (Urban and Rural) | Water |  | 1500000 |  | LLM
Appoint the Transactional Advisor – Zeeland WTW (Operational) | Water | 0 |  |  | LLM
Security Guard Houses | Water |  | 400000 |  | LLM
Office Equipment | Corporate Services | 500000 |  |  | LLM
Computer Equipment | Corporate Services | 300000 |  |  | LLM
Operationalisation testing ground/Weighbridge Town - Test ground | Social - Licencing | 1500000 |  |  | LLM
Licencing of Landfill | social - waste | 1800000 |  |  | LLM
1 X Compactor trucks | social - waste |  | 2000000 |  | LLM
1 x Skip loader truck | social - waste |  | 2500000 |  | LLM
Tractor | social - waste | 700000 |  |  | LLM
TLB + Detagible Broom | Public work | 1720000 |  |  | LLM
Trailor for Roller | Public work | 80000 |  |  | LLM
Road resealing | Public work | 2000000 |  |  | LLM
Marapong Roads & storm water Technical report | Public work | 1200000 |  |  | LLM
Onvewaght Roads -Technical report | Public work | 1200000 |  |  | LLM
Supply,Delivery and off - Loading on Mobile Trash Pump | Sanitation |  | 750000 |  | LLM
Supply,Delivery and off - Loading and licencing of Sewer Unblocking machine | Sanitation | 680000 |  |  | LLM
Supply delivery and Offloading of Mobile bucket winch | Sanitation | 1300000 |  |  | LLM
Refurbishment and upgrading of Paarl wastewater treatment works & holding dam | Sanitation | 1500000 |  |  | LLM
Technical report for VIP Toilets | Sanitation | 600000 |  |  | LLM
Refurbishment of Zongesien & construction of sewer dumping site | Sanitation | 2500000 |  |  | LLM
Construction of KingbirdLine (Techical report) | Electrical | 1600000 | 8000000 | 13500000 | LLM
Replacembet of Switch Gears x 2 | Electrical | 800000 |  |  | LLM
Consulting Engineer (Resposible Engineer - approval for Engineering) | Electrical |  |  |  | LLM
Maintanance and closing of the ring circuits + 12 | Electrical | 1000000 |  |  | LLM
Pump 25 Reurbishment and construction of line to zongesien | Sanitation | 500000 |  |  | LLM
Pump 24 Reurbishment and construction phehelelo | Sanitation |  | 2000000 |  | LLM
BI system | BTO | 300000 |  |  | LLM
LLM
TOTAL OWN FUNDING |  | 22030000 | 17150000 | 13500000
TOTAL CAPEX |  | 102396650.2 | 207176800.2 | 210369600
DESCRIPTION | 2023/24 | 2024/25 | 2025/26
Equtable share | 226374000 | 251551000 | 273787000
MIG | 2586000 | 2699300 | 2817400
FMG | 1700000 | 1700000 | 1900000
EPWP | 1035000
Total Operating Grants | 231695000 | 255950300 | 278504400
MIG | 49134000 | 51286700 | 53530600
ENERGY EFFICIENCY | 0 | 5000000 | 0
INEP | 0 | 18000000 | 18806000
WSIG | 0 | 52209000 | 54533000
WSIG S6B | 31226000 | 63531100 | 70000000
Own Funding Project | 22030000 | 17150000 | 13500000
TOTAL GRANTS | 102390000 | 207176800 | 210369600

## PROPOSED PROJECTS 2022-23 (2) (hidden)
CAPITAL PROJECTS - MIG
Description |  | Funder | 2022/23 | 2023/24 | 2024/25
Ga-Seleka and Witpoort RWS phase 5 (to be completed) | WATER | MIG | 13166148
Thabo Mbeki Sewer Network Sanitation PHASE2 | SANITATION | MIG | 22516008
Marapong (Phase 2) sports art and culture | PARKS | MIG | 10000000
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 10930242 |  |  |  | 10930242
Extension and Augmentation of water supply in Shongoane RWS Phase 6 | WATER | MIG |  | 49140650 | 51299050
TOTAL |  |  | 56612398 | 49140650 | 51299050
CAPITAL PROJETCS - WSIG
Refurbishment and Upgrading of Sewer Pump Stations, Network Pipes and Replacement of AC pipes in Town and Onverwacht | SANITATION | WSIG | 15000000
Replacement of AC pipes and Upgrading of Water Network in Marapong | WATER | WSIG | 10000000
Ground Water Scheme Development and Equipping of Boreholes in rural Node | WATER | WSIG | 10000000
Marapong Bulk Water Supply | WATER | WSIG | 22000000
Mokuruanyane RWS Bulk Pipeline | WATER | WSIG | 10160000
Refurbishment and upgrade of RWS in varios villages Phase 1 | WSIG SCHEDULE 5B | WSIG SCHEDULE 5B | 0 | 50832000 | 52209000
Refurbishment and upgrade of RWS in varios villages Phase 2 | WSIG SCHEDULE 6B | WSIG SCHEDULE 6B |  | 71226000 | 63531000
TOTAL |  |  | 67160000 | 122058000 | 115740000
CAPITAL PRIOJECT - INEP
Electrification of various villages, Marapong and Steenbokpan informal settlement |  | INEP | 20000000 | 22500000 | 10971000
TOTAL |  |  | 20000000 | 22500000 | 10971000
CAPITAL PRIOJECT - Energy Effeciency
town and villages |  | Energy Eff | 4000000 |  | 5000000
TOTAL |  |  | 4000000 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Review and Develop LED Strategy that ignite local economy | STRATEGIC SERVICES | LLM |  | 2000000
Lephalale Investment summit | STRATEGIC SERVICES | LLM |  | 2500000
Hawkers stalls Revitising the Economy | STRATEGIC SERVICES | LLM | 3500000 | 10000000
Branding of Municipal entrances | STRATEGIC SERVICES | LLM |  | 5000000
Lephalale vison 2040 3D prototype /Bankable Business case | STRATEGIC SERVICES | LLM |  | 5000000
Development of Lephalale Economic growth strategy for Vision 2050 | MM OFFICE | LLM | 5000000 | 2000000
Project management system | BTO | LLM | 480000 | 480000
Credit control system | BTO | LLM | 500000 | 500000
Indigent management system | BTO | LLM | 200000 | 300000
BI system & Revenue enhancement Tool | BTO | LLM | 500000 |  |  | billing accuracy /reporting
Anti-fraud and corruption hotline | RISK | LLM | 600000
Conduct security assessment of all strategic assets and implement appropriate security measures to protect the assets | SECURITY | LLM | 3000000
Mobile walk-through metal detector | SECURITY | LLM | 100000
Development of ICT strategy | IT | LLM | 1000000
Wireless and wired network- Data Centre | IT | LLM |  | 1500000
Implementation of shift system | Corporate | LLM | 0 |  |  | Operational (R2.5M)
Traffic Fine system (age analysis and administration) AAARTO ARRTIA System to be implemented | TRAFFIC | LLM |  | 200000 |  | Proposals
Formulation of General plans for villages. | PLANNING | LLM |  | 1000000
Revision of Spatial Development Framework | PLANNING | LLM | 1200000
Revison of Land use Scheme | PLANNING | LLM | 600000 | 600000
Revitalization of Marapong Township | PLANNING | LLM |  |  |  | 1000000 opex buling control
Land Acquisition | PLANNING | LLM |  | 5400000
Palisade Fencing for Onverwacht cemetery | PARKS | LLM | 2000000
Cover of sidewalk at civic centre for protection against the element | PUBLIC WORKS | LLM | 200000 |  |  | public works
Automated performance management system (for three-year period) |  | LLM |  | 1000000
2 x Tractor slasher mower | PARKS | LLM | 170000
2 X Chainsaws | PARKS | LLM | 28000
2 X Pole pruner chainsaw | PARKS | LLM | 32000
1 X LDV for Thusong centres | THUSONG & LIBRARY | LLM | 0 | 500000 |  | Unfunde mandate
1 x Sedan | TRAFFIC (New trainess ) | LLM | 400000
1 x LDV | TRAFFIC (New trainess ) | LLM |  | 500000 |  | public works
Branding, blue lights and siren | TRAFFIC (New trainess ) | LLM |  | 40000
Pro-laser for speed machine | TRAFFIC | LLM | 250000
5 X Firearms | TRAFFIC (New trainess ) | LLM |  | 100000
Revitalisation of Marapong township | PLANNING | LLM |  | 1000000 |  | Operational /Contracted
Development of a new institutional strategic plan till 2027 | PLANNING | LLM |  | 1000000 |  | Operational /Contracted
Weigh bridge system operationalize the one at waste(the other at traffic testing ground side) | TRAFFIC (New trainess ) | LLM | 400000
Acquisition of additional skip loader | Waste | LLM
Acquisition of 2 x compactor trucks | Waste | LLM
Acquisition of skip loader truck | Waste | LLM
Acquisition of additional 30 x skip bins | Waste | LLM |  | 3600000 |  | Provide costing - R28 00K Accerate Services .Flat rate and billing at the villages .Check the collection Prepaid metres
Brush Carters x 10 | PARKS | LLM | 150000
Installation of pump generators (Water Trucks)-3 | Water | LLM | 200000 |  |  | water
Installation of (2) water pumps spiral | Water | LLM | 150000 |  |  | water
Security guard houses | Water | LLM |  | 60000 |  | water
Ablution facility Witpoort | Water | LLM |  |  |  | Internal maintenance team
Office furniture | Water | LLM |  |  |  | Internal maintenance team
Water conservation and water demand management | Water | LLM |  | 1500000 |  | water
Installation of water Telemetric system | Water | LLM | 2500000 | 4500000 |  | water
Review water Conservation strategy | Water | LLM | 150000 |  |  | water
Leak detection and Repair Nertwork water leaks (pipe and valves) | Water | LLM | 1000000 |  |  | water
Civic centre diesel generator | Electricity | LLM | 1500000 |  |  | Electricity
Refurbishment of ablution facilities civic center | Public works | LLM |  |  |  | Internal maintenance team
Redesign and furniture for council chamber | Public works | LLM |  |  |  | Public works
Walk behind roller | Public works | LLM | 200000 |  |  | Public works
Plate compactor | Public works | LLM | 120000 |  |  | Public works
Crane truck | electricity | LLM |  |  |  | electricity
10 KVA Mobile diesel generator | electricity | LLM |  | 15000 |  | electricity
Cable fault detector | electricity | LLM | 700000 |  |  | electricity
Fencing of storage facilities | water | LLM | 500000 |  |  | water
Join a new Pipeline existig line from pumpstion 25 to zongesien | Sanitation | LLM | 500000 | 4500000 |  | sanitation
Assessment of zongesien, pumpstaion 25 | Sanitation | LLM | 500000 | 2500000 |  | sanitation
Mokuruanyane and Shongoane rws Phase 5 | Water | LLM | 0 | 8000000 |  | water
Melvel- drilling and equipping of borehole/ rising main/electrification | Water | LLM | 300000 | 500000 |  | water
Replacement of Furniture & Equipment | Corporate | LLM | 500000 |  |  | ALL
Mobile Office | BTO | LLM | 500000 |  |  | ALL
IT Equipment | IT | LLM | 300000 |  |  | ALL
OR Tambo
TOTAL |  |  | 29930000
Establishment of feedlot for farmers in rooigoed farm |  | PPP | 20000000
Agri-village |  | PPP | 15000000
Establishment of fresh produce Market |  | PPP | 20000000
Development of student accommodation |  | PPP | 250000000
University |  | ppp
OR Tambo |  | ppp | 50000000
Township and rural Economy |  | PPP | 210000000
Law enforcement stationary speed cameras |  | PPP | 500000
Zeeland water purification works Commitment |  | PPP | 53900000
Development of the Lephalale Design Framework proto – type(including review of SDF indicating development pattern of the city)procurement of urban design tool. |  | PPP | 5000000
TOTAL |  |  | 624400000
DBSA extension of Civic Centre Commitment |  | DBSA | 700000
TOTAL |  |  | 700000
Establishment of a learners testing centre at Mokuruanyane Thusong centre |  | DTCS | 5000000
TOTAL |  |  | 5000000
STALLED PROJECT : ON INTENDED
Zongesien R8M imparened. Value R5,4m need to ATTENDED TO - is there the need ? Critical Aborndedned project | [5 empty] | Service delivey for Marapong
Tranfer station legal process ? Any capex | [5 empty] | Service delivey for Marapong
Marapong reservor - how will the bulk line be supprted? Fully written off | [5 empty] | Service delivey for Marapong
PUMP STATION 25 Marapong - bandalised and stollen item - capitalise how to get to working condition - assessment PHASE 2 | [5 empty] | Service delivey for Marapong

## PROPOSED PROJECTS 2022-23 (3) (hidden)
CAPITAL PROJECTS - MIG
Description |  | Funder | 2022/23 | 2023/24 | 2024/25
Ga-Seleka and Witpoort RWS phase 5 (to be completed) | WATER | MIG | 13166148
Thabo Mbeki Sewer Network Sanitation PHASE2 | SANITATION | MIG | 22516008
Marapong (Phase 2) sports art and culture | PARKS | MIG | 10000000
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 10930242 |  |  |  | 10930242
Extension and Augmentation of water supply in Shongoane RWS Phase 6 | WATER | MIG |  | 49140650 | 51299050
TOTAL |  |  | 56612398 | 49140650 | 51299050
CAPITAL PROJETCS - WSIG
Refurbishment and Upgrading of Sewer Pump Stations, Network Pipes and Replacement of AC pipes in Town and Onverwacht | SANITATION | WSIG | 15000000
Replacement of AC pipes and Upgrading of Water Network in Marapong | WATER | WSIG | 10000000
Ground Water Scheme Development and Equipping of Boreholes in rural Node | WATER | WSIG | 10000000
Marapong Bulk Water Supply | WATER | WSIG | 22000000
Mokuruanyane RWS Bulk Pipeline | WATER | WSIG | 10160000
Refurbishment and upgrade of RWS in varios villages Phase 1 | WSIG SCHEDULE 5B | WSIG SCHEDULE 5B | 0 | 50832000 | 52209000
Refurbishment and upgrade of RWS in varios villages Phase 2 | WSIG SCHEDULE 6B | WSIG SCHEDULE 6B |  | 71226000 | 63531000
TOTAL |  |  | 67160000 | 122058000 | 115740000
CAPITAL PRIOJECT - INEP
Electrification of various villages, Marapong and Steenbokpan informal settlement |  | INEP | 20000000 | 22500000 | 10971000
TOTAL |  |  | 20000000 | 22500000 | 10971000
CAPITAL PRIOJECT - Energy Effeciency
town and villages |  | Energy Eff | 4000000 |  | 5000000
TOTAL |  |  | 4000000 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Review and Develop LED Strategy that ignite local economy | STRATEGIC SERVICES | LLM |  | 2000000
Lephalale Investment summit | STRATEGIC SERVICES | LLM |  | 2500000
Hawkers stalls Revitising the Economy | STRATEGIC SERVICES | LLM | 3500000 | 3500000
Branding of Municipal entrances | STRATEGIC SERVICES | LLM |  | 5000000
Lephalale vison 2040 3D prototype /Bankable Business case | STRATEGIC SERVICES | LLM |  | 5000000
Development of Lephalale Economic growth strategy for Vision 2050 | MM OFFICE | LLM | 5000000 | 2000000
Project management system | BTO | LLM | 480000 | 480000
Credit control system | BTO | LLM | 500000 | 500000
Indigent management system | BTO | LLM | 200000 | 300000
BI system & Revenue enhancement Tool | BTO | LLM | 500000 |  |  | billing accuracy /reporting
Anti-fraud and corruption hotline | RISK | LLM | 600000
Conduct security assessment of all strategic assets and implement appropriate security measures to protect the assets | SECURITY | LLM | 3000000
Mobile walk-through metal detector | SECURITY | LLM | 100000
Development of ICT strategy | IT | LLM | 1000000
Wireless and wired network- Data Centre | IT | LLM |  | 1500000
Traffic Fine system (age analysis and administration) AAARTO ARRTIA System to be implemented | TRAFFIC | LLM |  | 200000 |  | Proposals
Formulation of General plans for villages. | PLANNING | LLM |  | 1000000
Revision of Spatial Development Framework | PLANNING | LLM | 1200000
Revison of Land use Scheme | PLANNING | LLM | 600000 | 600000
Revitalization of Marapong Township | PLANNING | LLM |  |  |  | 1000000 opex buling control
Land Acquisition | PLANNING | LLM |  | 5400000
Palisade Fencing for Onverwacht cemetery | PARKS | LLM | 2000000
Cover of sidewalk at civic centre for protection against the element | PUBLIC WORKS | LLM | 200000 |  |  | public works
2 x Tractor slasher mower | PARKS | LLM | 170000
2 X Chainsaws | PARKS | LLM | 28000
2 X Pole pruner chainsaw | PARKS | LLM | 32000
1 X LDV for Thusong centres | THUSONG & LIBRARY | LLM | 0 | 500000 |  | Unfunde mandate
1 x Sedan | TRAFFIC (New trainess ) | LLM | 400000
1 x LDV | TRAFFIC (New trainess ) | LLM |  | 500000 |  | public works
Branding, blue lights and siren | TRAFFIC (New trainess ) | LLM |  | 40000
Pro-laser for speed machine | TRAFFIC | LLM | 250000
5 X Firearms | TRAFFIC (New trainess ) | LLM |  | 100000
Revitalisation of Marapong township | PLANNING | LLM |  | 1000000 |  | Operational /Contracted
Development of a new institutional strategic plan till 2027 | PLANNING | LLM |  | 1000000 |  | Operational /Contracted
Weigh bridge system operationalize the one at waste(the other at traffic testing ground side) | TRAFFIC (New trainess ) | LLM | 400000
Acquisition of additional 30 x skip bins | Waste | LLM |  | 3600000 |  | Provide costing - R28 00K Accerate Services .Flat rate and billing at the villages .Check the collection Prepaid metres
Brush Carters x 10 | PARKS | LLM | 150000
Installation of pump generators (Water Trucks)-3 | Water | LLM | 200000 |  |  | water
Installation of (2) water pumps spiral | Water | LLM | 150000 |  |  | water
Security guard houses | Water | LLM |  | 60000 |  | water
Water conservation and water demand management | Water | LLM |  | 1500000 |  | water
Installation of water Telemetric system | Water | LLM | 2250000 | 2250000 |  | water
Review water Conservation strategy | Water | LLM | 150000 |  |  | water
Leak detection and Repair Nertwork water leaks (pipe and valves) | Water | LLM | 1000000 |  |  | water
Civic centre diesel generator | Electricity | LLM | 1500000 |  |  | Electricity
Redesign and furniture for council chamber | Public works | LLM |  |  |  | Public works
Walk behind roller | Public works | LLM | 200000 |  |  | Public works
Plate compactor | Public works | LLM | 120000 |  |  | Public works
10 KVA Mobile diesel generator | electricity | LLM | 15000 |  |  | electricity
Cable fault detector | electricity | LLM | 700000 |  |  | electricity
Fencing of storage facilities | water | LLM | 500000 |  |  | water
Join a new Pipeline existig line from pumpstion 25 to zongesien | Sanitation | LLM | 500000 | 4500000 |  | sanitation
Assessment of zongesien, pumpstaion 25 | Sanitation | LLM | 500000 | 2500000 |  | sanitation
Mokuruanyane and Shongoane rws Phase 5 | Water | LLM | 0 | 8000000 |  | water
Melvel- drilling and equipping of borehole/ rising main/electrification | Water | LLM | 300000 | 500000 |  | water
Replacement of Furniture & Equipment | Corporate | LLM | 500000 |  |  | ALL
Mobile Office | BTO | LLM | 500000 |  |  | ALL
IT Equipment | IT | LLM | 300000 |  |  | ALL
TOTAL |  |  | 29695000 | 56030000 | 0
Establishment of feedlot for farmers in rooigoed farm |  | PPP | 20000000
Agri-village |  | PPP | 15000000
Establishment of fresh produce Market |  | PPP | 20000000
Development of student accommodation |  | PPP | 250000000
Satelite University RFQ |  | PPP | 0
OR Tambo |  | ppp | 50000000
Township and rural Economy |  | PPP | 210000000
Law enforcement stationary speed cameras |  | PPP | 500000
Zeeland water purification works Commitment |  | PPP | 53900000
Development of the Lephalale Design Framework proto – type(including review of SDF indicating development pattern of the city)procurement of urban design tool. |  | PPP | 5000000
OR Tambo |  | PPP | 50000000
TOTAL |  |  | 674400000
DBSA extension of Civic Centre Commitment |  | DBSA | 700000
TOTAL |  |  | 700000
Establishment of a learners testing centre at Mokuruanyane Thusong centre |  | DTCS | 5000000
TOTAL |  |  | 5000000
Introduction of flates
Flear Market
Advertising and Promontion

## PROCUREMENT PLAN 2022-23 (4) (hidden)
PROCUREMENT PLAN FOR 2022-2023
CAPITAL PROJECTS - MIG
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount | 2023/24 | 2024/25 | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | STATUS
Ga-Seleka and Witpoort RWS phase 5 (to be completed) | WATER | MIG | 13166148 | [6 empty] | In Progress
Thabo Mbeki Sewer Network Sanitation PHASE2 (In progress) | SANITATION | MIG | 17516008.3 | [6 empty] | In Progress
Marapong (Phase 2) sports art and culture | PARKS | MIG | 10000000 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Design Stage (EXXARO)
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 15930242.95 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Contractor Appointed | third quarter Jan | 15930242.95
Extension and Augmentation of water supply in Shongoane RWS Phase 6 | WATER | MIG | 0 | 49140650 | 51299050
TOTAL |  |  | 56612399.25 | 49140650 | 51299050
CAPITAL PROJETCS - WSIG
Refurbishment and Upgrading of Sewer Pump Stations, Network Pipes and Replacement of AC pipes in Town and Onverwacht | SANITATION | WSIG | 5809231 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Consultant Appointed
Replacement of AC pipes and Upgrading of Water Network in Marapong | WATER | WSIG | 3073099 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Consultant Appointed
Marapong Bulk Water Supply Storage | WATER | WSIG | 20992788 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Awarded
Marapong Bulk Water Supply | WATER | WSIG | 22719185 | [6 empty] | Awarded
Mokuruanyane RWS Bulk Pipeline | WATER | WSIG | 14565697 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Completed
Refurbishment and upgrade of RWS in varios villages Phase 1 | WSIG SCHEDULE 5B | WSIG SCHEDULE 5B | 0 | 50832000 | 52209000 |  |  |  |  | No Budget
Refurbishment and upgrade of RWS in varios villages Phase 2 | WSIG SCHEDULE 6B | WSIG SCHEDULE 6B |  | 71226000 | 63531000 | 15/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | No Budget
TOTAL |  |  | 67160000 | 122058000 | 115740000
CAPITAL PRIOJECT - INEP
Electrification of various villages, Marapong and Steenbokpan informal settlement |  | INEP | 20000000 | 22500000 | 10971000 | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Awarded
TOTAL |  |  | 20000000 | 22500000 | 10971000
CAPITAL PRIOJECT - Energy Effeciency
town and villages |  | LLM | 4000000 |  | 5000000 | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Awarded
TOTAL |  |  | 4000000 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Review and Develop LED Strategy that ignite local economy | STRATEGIC SERVICES | LLM |  | 2000000
Lephalale Investment summit | STRATEGIC SERVICES | LLM | 2500000 | 2500000 |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Awarded
Hawkers stalls Revitising the Economy | STRATEGIC SERVICES | LLM | 3500000 | 3500000
Branding of Municipal entrances | STRATEGIC SERVICES | LLM |  | 5000000
Lephalale vison 2040 3D prototype /Bankable Business case | STRATEGIC SERVICES | LLM |  | 5000000
Development of Lephalale Economic growth strategy for Vision 2050 | MM OFFICE | LLM | 5000000 | 2000000 |  | 01/07/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Advertised
Project management system | BTO | LLM | 480000 | 480000 |  | 01/07/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Pending Specification
Credit control system | BTO | LLM | 500000 | 500000 |  | 01/07/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | S.P withdrawn and project has be re-advertised
Indigent management system | BTO | LLM | 200000 | 300000 |  | 01/09/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Awarded
BI system & Revenue enhancement Tool | BTO | LLM | 500000 |  |  | 01/09/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | N/A
Anti-fraud and corruption hotline | RISK | LLM | 500000 |  |  | 01/07/2022 | 16/07/2022 | 29/07/2022 | 02/08/2022 | Awarded
Conduct security assessment of all strategic assets and implement appropriate security measures to protect the assets | SECURITY | LLM | 3000000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Awarded
Mobile walk-through metal detector | SECURITY | LLM | 100000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | RFQ | Under budgeted
Development of ICT strategy | IT | LLM | 1000000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Awarded | Third quarter
Wireless and wired network- Data Centre | IT | LLM |  | 1500000
Traffic Fine system (age analysis and administration) AAARTO ARRTIA System to be implemented | TRAFFIC | LLM |  | 200000
Formulation of General plans for villages. | PLANNING | LLM |  | 1000000
Revision of Spatial Development Framework | PLANNING | LLM | 1200000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Re-advertised
Revison of Land use Scheme | PLANNING | LLM | 600000 | 600000 |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Re-advertised
Revitalization of Marapong Township | PLANNING | LLM
Land Acquisition | PLANNING | LLM |  | 5400000
Palisade Fencing for Onverwacht cemetery | PARKS | LLM | 2000000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Awarded | Third quarter Jan
Cover of sidewalk at civic centre for protection against the element | PUBLIC WORKS | LLM | 200000 |  |  | 15/09/2022 | 30/09/2022 | 15/09/2022 | 30/10/2022 | Specification Pending | only 1 bidder responded,re-advertised
2 x Tractor slasher mower | PARKS | LLM | 170000 |  |  | 15/09/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | Awarded | third quarter
2 X Chainsaws | PARKS | LLM | 28000 |  |  | 01/07/2022 | 07/08/2022 | 30/08/2022 | 15/09/2022 | Awarded | third quarter
2 X Pole pruner chainsaw | PARKS | LLM | 32000 |  |  | 01/07/2022 | 07/08/2022 | 30/08/2022 | 15/09/2022 | Awarded | third quarter
1 X LDV for Thusong centres | THUSONG & LIBRARY | LLM |  | 500000
1 x Sedan | TRAFFIC (New trainess ) | LLM | 400000 |  |  | 01/10/2022 | 15/10/2022 | 30/10/2022 | 31/12/2022 | Quotation Requested from S.Ps (RT Contract)
1 x LDV | TRAFFIC (New trainess ) | LLM |  | 500000
Branding, blue lights and siren | TRAFFIC (New trainess ) | LLM |  | 40000
Pro-laser for speed machine | TRAFFIC | LLM | 250000 |  |  | 01/10/2022 | 15/10/2022 | 30/10/2022 | 31/12/2022 | Awarded
5 X Firearms | TRAFFIC (New trainess ) | LLM |  | 100000
Revitalisation of Marapong township | PLANNING | LLM |  | 1000000
Development of a new institutional strategic plan till 2027 | PLANNING | LLM |  | 1000000
Weigh bridge system operationalize the one at waste(the other at traffic testing ground side) | TRAFFIC (New trainess ) | LLM | 400000 |  |  | 01/10/2022 | 15/10/2022 | 30/10/2022 | 31/12/2022 | Re- Advert Closed awaiting Evaluation | Budget isssue
Acquisition of additional 30 x skip bins | Waste | LLM |  | 3600000
Brush Carters x 10 | PARKS | LLM | 150000 |  |  | 01/07/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | Awarded | Third quarter
Installation of pump generators (Water Trucks)-3 | Water | LLM | 200000 |  |  | 01/07/2022 | 19/07/2022 | 26/07/2022 | 30/08/2022 | Awarded
Installation of (2) water pumps spiral | Water | LLM | 150000 |  |  | 01/07/2022 | 19/07/2022 | 26/07/2022 | 30/08/2022 | Awarded | Kholo to facilitate
Security guard houses | Water | LLM |  | 60000
Water conservation and water demand management | Water | LLM |  | 1500000
Installation of water Telemetric system | Water | LLM | 2250000 | 2250000 |  | 01/07/2022 | 22/01/2023 | 08/02/2023 | 30/03/2023 | Specification Pending | End User confirmed that Funds were Moved
Review water Conservation strategy | Water | LLM | 150000 |  |  | 01/07/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | RFQ
Leak detection and Repair Nertwork water leaks (pipe and valves) | Water | LLM | 1000000 |  |  | 01/07/2022 | 10/01/2023 | 30/01/2023 | 28/02/2023 | Specification Pendind | End User confirmed that Funds were Moved
Civic centre diesel generator | Electricity | LLM | 1500000 |  |  | 01/7/2022 | 22/01/2023 | 16/02/2023 | 28/02/2023 | Procurement Diviation in Progress
Redesign and furniture for council chamber | Public works | LLM
Walk behind roller | Public works | LLM | 200000 |  |  | 01/08/2022 | 05/08/2022 | 17/08/2022 | 30/09/2022 | Quotations requested through RT Contract
Plate compactor | Public works | LLM | 120000 |  |  | 01/08/2022 | 05/08/2022 | 17/08/2022 | 30/09/2022 | Quotations requested through RT Contract
10 KVA Mobile diesel generator | electricity | LLM | 15000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | RFQ
Cable fault detector | electricity | LLM | 700000 |  |  | 01/09/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Awarded
2 X LDV Bakkie Canopies | electricity | LLM | 40000 |  |  | 01/07/2022 | 05/08/2022 | 30/08/202 | 15/09/2022 | Awarded
Fencing of storage facilities | water | LLM | 500000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Awarded
Join a new Pipeline existig line from pumpstion 25 to zongesien | Sanitation | LLM | 500000 | 4500000 |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | N/A | End User to be Notified (End User mentioned that Funds are not suffiecient to proceed with the project)
Assessment of zongesien, pumpstaion 25 | Sanitation | LLM | 500000 | 2500000 |  | 01/07/2022 | 31/07/2022 |  | 31/01/2023 | N/A | End User to be Notified (End User mentioned that Funds are not suffiecient to proceed with the project)
Mokuruanyane and Shongoane rws Phase 5 | Water | LLM | 0 | 8000000
Melvel- drilling and equipping of borehole/ rising main/electrification | Water | LLM | 300000 | 500000 |  | 01/03/2023 | 2023-10-03 | 24/03/2023 | 30/05/2023 | Awarded
Replacement of Furniture & Equipment | Corporate | LLM | 500000 |  |  | 01/03/2023 | 2023-10-03 | 24/03/2023 | 30/05/2023 | Advertised
Mobile Office | BTO | LLM | 500000 |  |  | 01/03/2023 | 2023-10-03 | 24/03/2023 | 30/05/2023 | Awaiting Evaluation
IT Equipment | IT | LLM | 300000 |  |  | 01/03/2023 | 2023-10-03 | 24/03/2023 | 30/05/2023 | Awarded
TOTAL |  |  | 32135000 | 56030000 | 0
Establishment of feedlot for farmers in rooigoed farm |  | PPP | 20000000
Agri-village |  | PPP | 15000000
Establishment of fresh produce Market |  | PPP | 20000000
Development of student accommodation |  | PPP | 250000000
Satelite University RFQ |  | PPP | 0
OR Tambo |  | ppp | 50000000
Township and rural Economy |  | PPP | 210000000
Law enforcement stationary speed cameras |  | PPP | 500000
Zeeland water purification works Commitment |  | PPP | 53900000
Development of the Lephalale Design Framework proto – type(including review of SDF indicating development pattern of the city)procurement of urban design tool. |  | PPP | 5000000
OR Tambo |  | PPP | 50000000
TOTAL |  |  | 674400000
DBSA extension of Civic Centre Commitment |  | DBSA | 700000
TOTAL |  |  | 700000
Establishment of a learners testing centre at Mokuruanyane Thusong centre |  | DTCS | 5000000
TOTAL |  |  | 5000000
Introduction of flates
Flear Market
Advertising and Promontion

## GRAND FUNDED
DORA ALLOCATION
DESCRIPTION | 2023/24 | 2024/25 | 2025/26 | TOTAL
Equtable share | 226374000 | 251551000 | 273787000 | 751712000
MIG- PMU | 2586000 | 2699300 | 2817400 | 8102700
FMG | 1700000 | 1700000 | 1900000 | 5300000
EPWP | 1035000 |  |  | 1035000
Total Operating Grants | 231695000 | 255950300 | 278504400 | 765114700
MIG | 49134000 | 51286700 | 53530600 | 153951300
ENERGY EFFICIENCY | 0 | 5000000 | 0 | 5000000
INEP | 0 | 18000000 | 18806000 | 36806000
WSIG | 0 | 52209000 | 54533000 | 106742000
WSIG S6B | 31226000 | 63531100 | 70000000 | 164757100
Total Operating Grants | 80360000 | 190026800 | 196869600
TOTAL GRANTS | 312055000 | 445977100 | 475374000 | 765114700

## PROCUREMENT PLAN 2023-2024
PROCUREMENT PLAN FOR 2023-2024
CAPITAL PROJECTS - MIG
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | Status
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 3892681.9 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 27/07/2023 | Awarded, In progress
Establishment of transfer stations in the rural villages | WASTE | MIG | 31980275.36 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 28/02/2024 | pending advert
Marapong sports, arts and culture precinct phase 2 | PARKS | MIG | 10000000 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 30/06/2024 | pending advert
Highmast installation in Various villages | ELECTRICITY | MIG | 3267692.94 | 11316727.78 |  | 14/5/2023 | 15/06/2023 | 29/06/2023 | 30/06/2024 | pending advert
TOTAL |  |  | 49140650.2 | 11316727.78 | 0
CAPITAL PROJETCS - WSIG
Marapong Bulk Water Supply Storage | WATER | WSIG | 10000000 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 30/06/2024 | awarded
Marapong Bulk Water Supply | WATER | WSIG | 21226000 |  |  | 24/07/2020 | 27/08/2020 | 01/09/2020 | 31/01/2024
TOTAL |  |  | 31226000 | 0 | 0
CAPITAL PRIOJECT - INEP
No Projects for 2023-2023
TOTAL |  |  | 0 | 0 | 0
CAPITAL PRIOJECT - Energy Effeciency
5000000
TOTAL |  |  | 0 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Asbestos Cutting Machine | Water | LLM | 100000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Jack Hammer (Makita Demolition Hammer) | Water | LLM | 150000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Computer Equipment | Corporate Services | LLM | 500000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Computer Equipment | Corporate Services | LLM | 300000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Operationalisation testing ground/Weighbridge Town - Test ground | Social - Licencing | LLM | 1500000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
Licencing of Landfill | Social - Licencing | LLM | 1800000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
1 X Compactor trucks | Strategic services | LLM |  | 5000000 | [5 empty] | Pending specifications
1 x Skip loader truck | MM's office | LLM |  | 2000000 |  | 01/07/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Pending specifications
Tractor | social - waste | LLM | 700000 | 480000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
TLB + Detagible Broom | Public work | LLM | 1720000 | 500000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
Trailor for Roller | Public work | LLM | 80000 | 300000 |  | 28/05/2023 | 13/06/2023 | 20/06/2023 | 30/08/2023 | Pending specifications
Road resealing | Public work | LLM | 2000000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
Marapong Roads & storm water Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Onvewaght Roads -Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading on Mobile Trash Pump | Sanitation | LLM | 0 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading and licencing of Sewer Unblocking machine | Sanitation | LLM | 680000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply delivery and Offloading of Mobile bucket winch | Sanitation | LLM | 1300000 | 1500000 |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Refurbishment and upgrading of Paarl wastewater treatment works & holding dam | Sanitation | LLM | 1500000 | 200000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Technical report for VIP Toilets | Sanitation | LLM | 600000 | 1000000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Refurbishment of Zongesien & construction of sewer dumping site | Sanitation | LLM | 2500000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Construction of KingbirdLine (Techical report) | Electrical | LLM | 1600000 | 600000 |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Replacembet of Switch Gears x 2 | Electrical | LLM | 800000 |  |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Consulting Engineer (Resposible Engineer - approval for Engineering) | Electrical | LLM | 0 | 5400000 | [5 empty] | Budgeted for 2024-2025
Maintanance and closing of the ring circuits + 12 | Electrical | LLM | 1000000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Pending specifications
Pump 25 Reurbishment and construction of line to zongesien | Sanitation | LLM | 500000 |  |  | 15/09/2022 | 30/09/2022 | 15/09/2022 | 30/10/2022 | Pending specifications
Pump 24 Reurbishment and construction phehelelo | Sanitation | LLM | 0 |  |  | 15/09/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | Pending specifications
BI system | BTO | LLM | 300000 |  |  | 01/07/2022 | 07/08/2022 | 30/08/2022 | 15/09/2022 | Pending specifications
TOTAL |  |  | 21780000 | 16980000 | 0

## PROCUREMENT PLAN 2023-2024 (2)
PROCUREMENT PLAN FOR 2023-2024
CAPITAL PROJECTS - MIG
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | Status
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 3892681.9 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 27/07/2023 | Awarded, In progress
Establishment of transfer stations in the rural villages | WASTE | MIG | 31980275.36 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 28/02/2024 | pending advert
Marapong sports, arts and culture precinct phase 2 | PARKS | MIG | 10000000 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 30/06/2024 | pending advert
Highmast installation in Various villages | ELECTRICITY | MIG | 3267692.94 | 11316727.78 |  | 14/5/2023 | 15/06/2023 | 29/06/2023 | 30/06/2024 | pending advert
TOTAL |  |  | 49140650.2 | 11316727.78 | 0
CAPITAL PROJETCS - WSIG
Marapong Bulk Water Supply Storage | WATER | WSIG | 10000000 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 30/06/2024 | awarded
Marapong Bulk Water Supply | WATER | WSIG | 21226000 |  |  | 24/07/2020 | 27/08/2020 | 01/09/2020 | 31/01/2024
TOTAL |  |  | 31226000 | 0 | 0
CAPITAL PRIOJECT - INEP
No Projects for 2023-2023
TOTAL |  |  | 0 | 0 | 0
CAPITAL PRIOJECT - Energy Effeciency
5000000
TOTAL |  |  | 0 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date
Asbestos Cutting Machine | Water | LLM | 100000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Jack Hammer (Makita Demolition Hammer) | Water | LLM | 150000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Office Equipment | Corporate Services | LLM | 500000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Computer Equipment | Corporate Services | LLM | 300000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Operationalisation testing ground/Weighbridge Town - Test ground | Social - Licencing | LLM | 1500000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
Appoint the Transactional Advisor – Zeeland WTW | Water | LLM/PPP | 500000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Appoint the Transactional Advisor – Grey Water | Sanitation | LLM/PPP | 500000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Licencing of Landfill | Social - Licencing | LLM | 800000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
1 X Compactor trucks | Strategic services | LLM |  | 5000000 | [5 empty] | Pending specifications
1 x Skip loader truck | MM's office | LLM |  | 2000000 |  | 01/07/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Pending specifications
Tractor | social - waste | LLM | 700000 | 480000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
TLB + Detagible Broom | Public work | LLM | 1720000 | 500000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Trailor for Roller | Public work | LLM | 80000 | 300000 |  | 28/05/2023 | 13/06/2023 | 20/06/2023 | 30/08/2023 | Pending specifications
Road resealing | Public work | LLM | 1000000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Marapong Roads & storm water Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Onvewaght Roads -Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading on Mobile Trash Pump | Sanitation | LLM | 0 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading and licencing of Sewer Unblocking machine | Sanitation | LLM | 680000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply delivery and Offloading of Mobile bucket winch | Sanitation | LLM | 1300000 | 1500000 |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Refurbishment and upgrading of Paarl wastewater treatment works & holding dam | Sanitation | LLM | 1500000 | 200000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Technical report for VIP Toilets | Sanitation | LLM | 600000 | 1000000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Refurbishment of Zongesien & construction of sewer dumping site | Sanitation | LLM | 1500000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Construction of KingbirdLine (Techical report) | Electrical | LLM | 1600000 | 600000 |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Replacembet of Switch Gears x 2 | Electrical | LLM | 800000 |  |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Consulting Engineer (Resposible Engineer - approval for Engineering) | Electrical | LLM | 0 | 5400000 | [5 empty] | Budgeted for 2024-2025
Maintanance and closing of the ring circuits + 12 | Electrical | LLM | 1000000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Pending specifications
Pump 25 Reurbishment and construction of line to zongesien | Sanitation | LLM | 500000 |  |  | 15/09/2022 | 30/09/2022 | 15/09/2022 | 30/10/2022 | Pending specifications
Pump 24 Reurbishment and construction phehelelo | Sanitation | LLM | 0 |  |  | 15/09/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | Pending specifications
BI system | BTO | LLM | 300000 |  |  | 01/07/2022 | 07/08/2022 | 30/08/2022 | 15/09/2022 | Pending specifications
OR Tambo dual line Road Design and Technical Report | Public work | LLM/PPP | 1000000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Solar Plant Technical Assessment | Electrical | LLM/PPP | 1000000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
TOTAL |  |  | 22030000 | 16980000 | 0

## PROCUREMENT PLAN 2023-2024 (3)
PROCUREMENT PLAN FOR 2023-2024
CAPITAL PROJECTS - MIG
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | Status
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 3892681.9 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 27/07/2023 | Awarded, In progress
Establishment of transfer stations in the rural villages | WASTE | MIG | 31980275.36 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 28/02/2024 | pending advert
Marapong sports, arts and culture precinct phase 2 | PARKS | MIG | 10000000 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 30/06/2024 | pending advert
Highmast installation in Various villages | ELECTRICITY | MIG | 3267692.94 | 11316727.78 |  | 14/5/2023 | 15/06/2023 | 29/06/2023 | 30/06/2024 | pending advert
TOTAL |  |  | 49140650.2 | 11316727.78 | 0
CAPITAL PROJETCS - WSIG
Marapong Bulk Water Supply Storage | WATER | WSIG | 10000000 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 30/06/2024 | awarded
Marapong Bulk Water Supply | WATER | WSIG | 21226000 |  |  | 24/07/2020 | 27/08/2020 | 01/09/2020 | 31/01/2024
TOTAL |  |  | 31226000 | 0 | 0
CAPITAL PRIOJECT - INEP
No Projects for 2023-2023
TOTAL |  |  | 0 | 0 | 0
CAPITAL PRIOJECT - Energy Effeciency
5000000
TOTAL |  |  | 0 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date
Asbestos Cutting Machine | Water | LLM | 100000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Jack Hammer (Makita Demolition Hammer) | Water | LLM | 150000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Office Equipment | Corporate Services | LLM | 500000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Computer Equipment | Corporate Services | LLM | 300000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Operationalisation testing ground/Weighbridge Town - Test ground | Social - Licencing | LLM | 1500000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
Appoint the Transactional Advisor – Zeeland WTW | Water | LLM/PPP | 500000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Appoint the Transactional Advisor – Grey Water | Sanitation | LLM/PPP | 500000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Licencing of Landfill | Social - Licencing | LLM | 800000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
1 X Compactor trucks | Strategic services | LLM |  | 5000000 | [5 empty] | Pending specifications
1 x Skip loader truck | MM's office | LLM |  | 2000000 |  | 01/07/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Pending specifications
Tractor | social - waste | LLM | 700000 | 480000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
TLB + Detagible Broom | Public work | LLM | 1720000 | 500000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Trailor for Roller | Public work | LLM | 80000 | 300000 |  | 28/05/2023 | 13/06/2023 | 20/06/2023 | 30/08/2023 | Pending specifications
Road resealing | Public work | LLM | 1000000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Marapong Roads & storm water Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Onvewaght Roads -Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading on Mobile Trash Pump | Sanitation | LLM | 0 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading and licencing of Sewer Unblocking machine | Sanitation | LLM | 680000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply delivery and Offloading of Mobile bucket winch | Sanitation | LLM | 1300000 | 1500000 |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Refurbishment and upgrading of Paarl wastewater treatment works & holding dam | Sanitation | LLM | 1500000 | 200000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Technical report for VIP Toilets | Sanitation | LLM | 600000 | 1000000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Refurbishment of Zongesien & construction of sewer dumping site | Sanitation | LLM | 1500000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Construction of KingbirdLine (Techical report) | Electrical | LLM | 1600000 | 600000 |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Replacembet of Switch Gears x 2 | Electrical | LLM | 800000 |  |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Consulting Engineer (Resposible Engineer - approval for Engineering) | Electrical | LLM | 0 | 5400000 | [5 empty] | Budgeted for 2024-2025
Maintanance and closing of the ring circuits + 12 | Electrical | LLM | 1000000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Pending specifications
Pump 25 Reurbishment and construction of line to zongesien | Sanitation | LLM | 500000 |  |  | 15/09/2022 | 30/09/2022 | 15/09/2022 | 30/10/2022 | Pending specifications
Pump 24 Reurbishment and construction phehelelo | Sanitation | LLM | 0 |  |  | 15/09/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | Pending specifications
BI system | BTO | LLM | 300000 |  |  | 01/07/2022 | 07/08/2022 | 30/08/2022 | 15/09/2022 | Pending specifications
OR Tambo dual line Road Design and Technical Report | Public work | LLM/PPP | 1000000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Solar Plant Technical Assessment | Electrical | LLM/PPP | 1000000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
TOTAL |  |  | 22030000 | 16980000 | 0

## PROCUREMENT PLAN 2023-2024 (4) (hidden)
PROCUREMENT PLAN FOR 2023-2024
CAPITAL PROJECTS - MIG
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | Status
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 3892681.9 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 27/07/2023 | Awarded, In progress
Establishment of transfer stations in the rural villages | WASTE | MIG | 31980275.36 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 28/02/2024 | pending advert
Marapong sports, arts and culture precinct phase 2 | PARKS | MIG | 10000000 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 30/06/2024 | pending advert
Highmast installation in Various villages | ELECTRICITY | MIG | 3267692.94 | 11316727.78 |  | 14/5/2023 | 15/06/2023 | 29/06/2023 | 30/06/2024 | pending advert
TOTAL |  |  | 49140650.2 | 11316727.78 | 0
CAPITAL PROJETCS - WSIG
Marapong Bulk Water Supply Storage | WATER | WSIG | 10000000 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 30/06/2024 | awarded
Marapong Bulk Water Supply | WATER | WSIG | 21226000 |  |  | 24/07/2020 | 27/08/2020 | 01/09/2020 | 31/01/2024
TOTAL |  |  | 31226000 | 0 | 0
CAPITAL PRIOJECT - INEP
No Projects for 2023-2023
TOTAL |  |  | 0 | 0 | 0
CAPITAL PRIOJECT - Energy Effeciency
5000000
TOTAL |  |  | 0 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date
Asbestos Cutting Machine | Water | LLM | 100000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Jack Hammer (Makita Demolition Hammer) | Water | LLM | 150000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Office Equipment | Corporate Services | LLM | 500000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Computer Equipment | Corporate Services | LLM | 300000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Operationalisation testing ground/Weighbridge Town - Test ground | Social - Licencing | LLM | 1500000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
Appoint the Transactional Advisor – Zeeland WTW | Water | LLM/PPP | 500000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Appoint the Transactional Advisor – Grey Water | Sanitation | LLM/PPP | 500000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Licencing of Landfill | Social - Licencing | LLM | 800000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
1 X Compactor trucks | Strategic services | LLM |  | 5000000 | [5 empty] | Pending specifications
1 x Skip loader truck | MM's office | LLM |  | 2000000 |  | 01/07/2022 | 15/09/2022 | 30/09/2022 | 28/02/2023 | Pending specifications
Tractor | social - waste | LLM | 700000 | 480000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
TLB + Detagible Broom | Public work | LLM | 1720000 | 500000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Trailor for Roller | Public work | LLM | 80000 | 300000 |  | 28/05/2023 | 13/06/2023 | 20/06/2023 | 30/08/2023 | Pending specifications
Road resealing | Public work | LLM | 1000000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Marapong Roads & storm water Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Onvewaght Roads -Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading on Mobile Trash Pump | Sanitation | LLM | 0 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Subtotal |  |  | 10250000
Supply,Delivery and off - Loading and licencing of Sewer Unblocking machine | Sanitation | LLM | 680000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply delivery and Offloading of Mobile bucket winch | Sanitation | LLM | 1300000 | 1500000 |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Refurbishment and upgrading of Paarl wastewater treatment works & holding dam | Sanitation | LLM | 1500000 | 200000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Technical report for VIP Toilets | Sanitation | LLM | 600000 | 1000000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Refurbishment of Zongesien & construction of sewer dumping site | Sanitation | LLM | 1500000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Construction of KingbirdLine (Techical report) | Electrical | LLM | 1600000 | 600000 |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Replacembet of Switch Gears x 2 | Electrical | LLM | 800000 |  |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Consulting Engineer (Resposible Engineer - approval for Engineering) | Electrical | LLM | 0 | 5400000 | [5 empty] | Budgeted for 2024-2025
Maintanance and closing of the ring circuits + 12 | Electrical | LLM | 1000000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Pending specifications
Pump 25 Reurbishment and construction of line to zongesien | Sanitation | LLM | 500000 |  |  | 15/09/2022 | 30/09/2022 | 15/09/2022 | 30/10/2022 | Pending specifications
Pump 24 Reurbishment and construction phehelelo | Sanitation | LLM | 0 |  |  | 15/09/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | Pending specifications
BI system | BTO | LLM | 300000 |  |  | 01/07/2022 | 07/08/2022 | 30/08/2022 | 15/09/2022 | Pending specifications
OR Tambo dual line Road Design and Technical Report | Public work | LLM/PPP | 1000000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Solar Plant Technical Assessment | Electrical | LLM/PPP | 1000000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
OR Tambo dual line Road Design and Technical Report | Public work | 1000000 | 1000000
Solar Plant Technical Assessment | Electrical | 1200000 | 1200000
Appoint the Transactional Advisor – Zeeland WTW | Water | 1300000 | 1300000
Appoint the Transactional Advisor – Grey Water | Sanitation | 1300000 | 1300000
Subtotal |  |  | 11780000
TOTAL |  |  | 22030000 | 16980000 | 0

## PROCUREMENT PLAN 2023-2024 (5)
PROCUREMENT PLAN FOR 2023-2024
CAPITAL PROJECTS - MIG
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | Status
Extension and Augmentation of water supply in Witpoort RWS 6 | WATER | MIG | 3892681.9 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 27/07/2023 | Awarded, In progress
Establishment of transfer stations in the rural villages | WASTE | MIG | 31980275.36 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 28/02/2024 | pending advert
Marapong sports, arts and culture precinct phase 2 | PARKS | MIG | 10000000 |  |  | 14/05/2023 | 15/06/2023 | 28/06/2023 | 30/06/2024 | pending advert
Highmast installation in Various villages | ELECTRICITY | MIG | 3267692.94 | 11316727.78 |  | 14/5/2023 | 15/06/2023 | 29/06/2023 | 30/06/2024 | pending advert
TOTAL |  |  | 49140650.2 | 11316727.78 | 0
CAPITAL PROJETCS - WSIG
Marapong Bulk Water Supply Storage | WATER | WSIG | 10000000 |  |  | 15/07/2022 | 31/07/2022 | 15/08/2022 | 30/06/2024 | awarded
Marapong Bulk Water Supply | WATER | WSIG | 21226000 |  |  | 24/07/2020 | 27/08/2020 | 01/09/2020 | 31/01/2024
TOTAL |  |  | 31226000 | 0 | 0
CAPITAL PRIOJECT - INEP
No Projects for 2023-2023
TOTAL |  |  | 0 | 0 | 0
CAPITAL PRIOJECT - Energy Effeciency
5000000
TOTAL |  |  | 0 | 0 | 5000000
CAPITAL PROJECT - OWN FUNDING
Description | Department / Division | Funder | Estimated Cost (R)/ Budgeted Amount 2023-2024 | 2024/25 | 2025/26 | Preperation of BD/RFQ date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date
Asbestos Cutting Machine | Water | LLM | 100000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Jack Hammer (Makita Demolition Hammer) | Water | LLM | 150000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Office Equipment | Corporate Services | LLM | 500000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Computer Equipment | Corporate Services | LLM | 300000 |  |  | 06/06/2023 | 20/06/2023 | 30/06/2023 | 30/08/2023 | Pending specifications
Operationalisation testing ground/Weighbridge Town - Test ground | Social - Licencing | LLM | 1500000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
Appoint the Transactional Advisor – Zeeland WTW | Water | LLM/PPP | 1300000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Appoint the Transactional Advisor – Grey Water | Sanitation | LLM/PPP | 1300000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Licencing of Landfill | Social - Licencing | LLM | 1500000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
1 X Compactor trucks | Strategic services | LLM |  | 5000000 | [5 empty] | Pending specifications
1 x Skip loader truck | MM's office | LLM |  | 2000000 | [5 empty] | Pending specifications
Tractor | social - waste | LLM | 700000 | 480000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/09/2023 | Pending specifications
TLB + Detagible Broom | Public work | LLM | 1720000 | 500000 |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Trailor for Roller | Public work | LLM | 80000 | 300000 |  | 28/05/2023 | 13/06/2023 | 20/06/2023 | 30/08/2023 | Pending specifications
Road resealing | Public work | LLM | 2000000 |  |  | 14/05/2023 | 28/05/2023 | 30/06/2023 | 30/12/2023 | Pending specifications
Marapong Roads & storm water Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Onvewaght Roads -Technical report | Public work | LLM | 1200000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply,Delivery and off - Loading on Mobile Trash Pump | Sanitation | LLM | 0 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Subtotal |  |  | 13550000
Supply,Delivery and off - Loading and licencing of Sewer Unblocking machine | Sanitation | LLM | 680000 |  |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Supply delivery and Offloading of Mobile bucket winch | Sanitation | LLM | 1300000 | 1500000 |  | 01/07/2023 | 16/07/2023 | 29/07/2023 | 30/08/2023 | Pending specifications
Refurbishment and upgrading of Paarl wastewater treatment works & holding dam | Sanitation | LLM | 1500000 | 200000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Technical report for VIP Toilets | Sanitation | LLM | 600000 | 1000000 |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Refurbishment of Zongesien & construction of sewer dumping site | Sanitation | LLM | 2000000 |  |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Construction of KingbirdLine (Techical report) | Electrical | LLM | 1600000 | 600000 |  | 15/10/2022 | 30/10/2022 | 15/11/2022 | 28/02/2023 | Pending specifications
Replacembet of Switch Gears x 2 | Electrical | LLM | 800000 |  |  | 06/06/2023 | 26/06/2023 | 15/07/2023 | 30/09/2023 | Pending specifications
Consulting Engineer (Resposible Engineer - approval for Engineering) | Electrical | LLM | 0 | 5400000 | [5 empty] | Budgeted for 2024-2025
Maintanance and closing of the ring circuits + 12 | Electrical | LLM | 1000000 |  |  | 01/07/2022 | 31/07/2022 | 15/08/2022 | 31/01/2023 | Pending specifications
Pump 25 Reurbishment and construction of line to zongesien | Sanitation | LLM | 500000 |  |  | 15/09/2022 | 30/09/2022 | 15/09/2022 | 30/10/2022 | Pending specifications
Pump 24 Reurbishment and construction phehelelo | Sanitation | LLM | 0 |  |  | 15/09/2022 | 17/09/2022 | 27/09/2022 | 27/10/2022 | Pending specifications
BI system | BTO | LLM | 300000 |  |  | 01/07/2022 | 07/08/2022 | 30/08/2022 | 15/09/2022 | Pending specifications
OR Tambo dual line Road Design and Technical Report | Public work | LLM/PPP | 1300000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
Solar Plant Technical Assessment | Electrical | LLM/PPP | 1200000 |  |  | 22/05/2023 | 31/05/2023 | 30/06/2023 | 30/12/2023
SUBTOTAL |  |  | 12780000
TOTAL OWN FUNDING |  |  | 26330000 | 16980000 | 0
TOTAL PROJECTS |  |  | 106696650.2